## List
| Dex |  | Bhadz |  | Don |  | Kynth
MUR | API Branch list - 4 API Business list - 3 API Advance search - 5 | 12 | BOSS extract transaction report, save in DB and backup in S3 - 10 UI Branch list - 5 UI Business list - 5 UI Advance search - 10 | 20 |  |  | S3 access - boss
Dongle Tracker |  |  | API Add - 3 API Edit - 3 API Delete - 3 | 24 | API Batch Upload Dongles - 4 UI Batch Upload Dongles - 4 UI Add - 5 UI Edit - 5 UI Delete - 5 | 23
Partner, Sales Channel and Account Owner Management |  |  | API - Integrate in Merchant Tab - 4 UI - Integrate in Merchant Tab - 5 API Add - 2 API Edit - 2 API Delete - 2 UI Add in Configuration Tab - 4 UI Edit in Configuration Tab - 4 UI Delete in Configuration Tab - 4
Expansion of Callout Queue | Database - add status - 4 UI - 10 | 14 |  |  |  |  | Remarks: only 9th can go back to 1st callout.
Add Negative Scenario Queues | Database - add status - 4 | 4 |  |  |  |  | Remarks: Both business and branch
SLA and Aging | Queues - UI -10 Queues - API -10 Configuration SLA (Rules) - UI -20 Configuration SLA (Rules) - API -20 Merchant - API -5 | 65
Merchant On-Boarding History | API - 5 | 5 |  |  | UI - integrate in Merchant and Queues - 5 | 5
Additional KYM Functionalities | API - Configuration for Schedule - 6 API - Update logic of create/update business/branch - 7 | 13 |  |  | UI - 7 | 7 | Remarks: kym schedule is selected branch status will automatically go to "kym schedule" this is true if the branch status seleted is below "kym visit"
Move Comments Field to Business Documents Section |  |  | UI - (business - before doc) - 5 Database (with bulk)- 10 | 15
Add Philippine Standard Industry Classification (PSIC) Field |  |  | API - configuration for mapping - 6 UI - configuration for mapping - 6 | 12 | UI - integrate in business information - 4 | 8 | Remarks: configuration - add mcc (for mapping)
Transaction Limits | API - App - 4 API - Admin Portal to Swiff - 5 | 9 | Android App FE- 2 | 2 | IOS App FE - 2 | 2
Alignment of Globe Charge registration channels | API - 8 | 8
Data Dump to and from BOSS |  |  | Merchant data dump sending to BOSS - 8 | 8
LB auto-shifting APP |  |  | Android RND - 3 Android implem - 3 | 6 | IOS RND - 3 IOS implem - 2 | 5
|  | 130 |  | 87 |  | 50
|  | 4.3333 |  | 2.9 |  | 1.6667

## Calendar
QA | Dex | Bhadz | July | [30 empty] | August | [30 empty] | September | [29 empty] | October | [29 empty] | November | [29 empty] | December
Dhino | Don | Globe Portal | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| MUR - Oct 21 | Firewall from BOSS to AWS | bar: July 6 to July 10; July 13 to July 17; July 20 to July 24; July 27 to July 31; August 3 to August 7
BOSS extract transaction report, save in DB and backup in S3 - 10 | bar: July 3; July 6 to July 10; July 13 to July 17
API Branch list - 4 | bar: July 3; July 20 to July 23
API Business list - 3 | bar: July 3; July 24; July 27 to July 28
API Advance search - 5 | bar: July 3; July 29 to July 31; August 3 to August 4
UI Branch list - 5 | bar: August 5 to August 7; August 10 to August 11
UI Business list - 5 | bar: July 3; August 12 to August 14; August 17 to August 18
UI Advance search - 10 | bar: July 3; August 19 to August 21; August 24 to August 28; August 31 to September 4
QA - 10 | bar: July 3; September 7 to September 11; September 14 to September 18
RFS | bar: July 1 to September 23
| Dongle - Sept 16 | API Add - 3 | bar: July 20 to July 22
API Edit - 3 | bar: July 23 to July 24; July 27
API Delete - 3 | bar: July 28 to July 30
UI Add - 5 | bar: July 3; July 27 to July 31
UI Edit - 5 | bar: July 3; August 3 to August 7
UI Delete - 5 | bar: July 3; August 10 to August 14
API Batch Upload Dongles - 4 | bar: July 3; August 17 to August 20
UI Batch Upload Dongles - 4 | bar: August 21; August 24 to August 27
QA - 10 | bar: August 31 to September 4; September 7 to September 11
RFS | bar: July 1 to September 16
| SLA and Aging - Nov 12 | Queues - API -10 | bar: July 3; July 6 to July 10; July 13 to July 17
Queues - UI -10 | bar: July 3; August 5 to August 7; August 10 to August 14; August 17 to August 18
Configuration SLA (Rules) - API - 20 | bar: July 3; August 19 to August 21; August 24 to August 28; August 31 to September 4; September 7 to September 11; September 14 to September 15
Configuration SLA (Rules) - UI - 20 | bar: July 3; September 16 to September 18; September 21 to September 25; September 28 to October 2; October 5 to October 9; October 12 to October 13
Merchant - API - 5 | bar: October 14 to October 16; October 19 to October 23
QA - 10 | bar: October 26 to October 30; November 3 to November 7
RFS | bar: July 1 to November 26
| Partner, Sales Channel and Account Owner Management - Oct 28 | API - Integrate in Merchant Tab - 4 | bar: July 3; September 2 to September 4; September 7
UI - Integrate in Merchant Tab - 5 | bar: July 3; September 8 to September 11; September 14
API Add - 2 | bar: July 3; September 15 to September 16
API Edit - 2 | bar: July 3; September 17 to September 18
API Delete - 2 | bar: September 21 to September 22
UI Add in Configuration Tab - 4 | bar: September 23 to September 25; September 28
UI Edit in Configuration Tab - 4 | bar: July 3; September 29 to October 2
UI Delete in Configuration Tab - 4 | bar: July 3; October 5 to October 9
QA - 10 | bar: July 3; October 12 to October 16; October 19 to October 23
RFS | bar: July 1 to October 28
| Merchant On-Boarding History - Nov 26 | API - 5 | bar: October 21 to October 23; October 26 to October 27
UI - integrate in Merchant and Queues - 5 | bar: October 28 to October 30; November 3 to November 7
QA - 10 | bar: November 10 to November 14; November 17 to November 21
RFS | bar: July 1 to November 26
| Expansion of Callout Queue - Nov 26 | Database - add status - 4 | bar: October 28 to October 30; November 3
UI - 10 | bar: November 4 to November 7; November 10
QA - 10 | bar: November 11 to November 14; November 17 to November 21
RFS | bar: July 1 to November 26
| Add Negative Scenario Queues | Database - add status - 4 | bar: July 3; July 6 to July 10
QA - 5 | bar: July 3; July 13 to July 17
RFS | bar: July 1 to September 16
| Additional KYM Functionalities - Oct 21 | API - Configuration for Schedule - 6 | bar: July 3; August 17 to August 21; August 24
API - Update logic of create/update business/branch - 7 | bar: August 6 to August 7; August 10 to August 14
UI - 7 | bar: August 25 to August 28; August 31 to September 4
QA - 10 | bar: September 7 to September 11; September 14 to September 18
RFS | bar: July 1 to September 23
| Move Comments Field to Business Documents Section | UI - (business - before doc) - 5 Database - 10 | bar: October 12 to October 16; October 19 to October 23; October 26 to October 30
QA - 10 | bar: November 3 to November 7; November 10 to November 14
RFS | bar: July 1 to November 19
| Add Philippine Standard Industry Classification (PSIC) Field | API - configuration for mapping - 5 | bar: July 3; September 7 to September 11
UI - configuration for mapping - 5 | bar: July 3; September 14 to September 18
UI - integrate in business information - 5 | bar: July 3; September 21 to September 25
QA - 10 | bar: September 28 to October 2; October 5 to October 9
x
| Transaction Limits | API - App - 4 | bar: November 11 to November 14
API - Admin Portal to Swiff - 5 | bar: November 17 to November 21
Android App FE- 2 | bar: July 3; November 17 to November 18
IOS App FE - 2 | bar: July 3; November 17 to November 18
QA - 10 | bar: November 24 to November 28
RFS | bar: July 1 to December 3
| Alignment of Globe Charge registration channels | API -5 | bar: July 3; August 10 to August 14
Globe Portal UI | bar: July 3
QA - 10
RFS | bar: July 1 to August 25
| LB auto-shifting APP | Android RND - 3 | bar: July 3; November 3 to November 5
Android implem - 3 | bar: July 3; November 6 to November 7; November 10 to November 14
IOS RND - 3 | bar: July 3; November 5 to November 7
IOS implem - 2 | bar: November 10 to November 14
QA - 10 | bar: November 17 to November 21
RFS | bar: July 1 to November 26

## Copy of Calendar
QA | Dex | Bhadz | July | [30 empty] | August | [30 empty] | September | [29 empty] | October | [29 empty] | November | [29 empty] | December
Dhino | Don | Globe Portal | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| MUR - Oct 21 | Firewall from BOSS to AWS | bar: July 6 to July 10; July 13 to July 17; July 20 to July 24; July 27 to July 31; August 3 to August 7
BOSS extract transaction report, save in DB and backup in S3 - 10 | bar: July 3; July 6 to July 10; July 13 to July 17
API Branch list - 4 | bar: July 3; July 20 to July 23
API Business list - 3 | bar: July 3; July 24; July 27 to July 28
API Advance search - 5 | bar: July 3; July 29 to July 31; August 3 to August 4
UI Branch list - 5 | bar: August 5 to August 7; August 10 to August 11
UI Business list - 5 | bar: July 3; August 12 to August 14; August 17 to August 18
UI Advance search - 10 | bar: July 3; August 19 to August 21; August 24 to August 28; August 31 to September 4
QA - 10 | bar: July 3; September 7 to September 11; September 14 to September 18
RFS | bar: July 1 to September 23
| Dongle - Sept 16 | API Add - 3 | bar: July 20 to July 22
API Edit - 3 | bar: July 23 to July 24; July 27
API Delete - 3 | bar: July 28 to July 30
UI Add - 5 | bar: July 3; July 27 to July 31
UI Edit - 5 | bar: July 3; August 3 to August 7
UI Delete - 5 | bar: July 3; August 10 to August 14
API Batch Upload Dongles - 4 | bar: July 3; August 17 to August 20
UI Batch Upload Dongles - 4 | bar: August 21; August 24 to August 27
QA - 10 | bar: August 31 to September 4; September 7 to September 11
RFS | bar: July 1 to September 16
| SLA and Aging - Nov 12 | Queues - API -10 | bar: July 3; July 6 to July 10; July 13 to July 17
Queues - UI -10 | bar: July 3; August 5 to August 7; August 10 to August 14; August 17 to August 18
Configuration SLA (Rules) - API - 20 | bar: July 3; August 19 to August 21; August 24 to August 28; August 31 to September 4; September 7 to September 11; September 14 to September 15
Configuration SLA (Rules) - UI - 20 | bar: July 3; September 16 to September 18; September 21 to September 25; September 28 to October 2; October 5 to October 9; October 12 to October 13
Merchant - API - 5 | bar: October 14 to October 16; October 19 to October 23
QA - 10 | bar: October 26 to October 30; November 3 to November 7
RFS | bar: July 1 to November 26
| Partner, Sales Channel and Account Owner Management - Oct 28 | API - Integrate in Merchant Tab - 4 | bar: July 3; September 2 to September 4; September 7
UI - Integrate in Merchant Tab - 5 | bar: July 3; September 8 to September 11; September 14
API Add - 2 | bar: July 3; September 15 to September 16
API Edit - 2 | bar: July 3; September 17 to September 18
API Delete - 2 | bar: September 21 to September 22
UI Add in Configuration Tab - 4 | bar: September 23 to September 25; September 28
UI Edit in Configuration Tab - 4 | bar: July 3; September 29 to October 2
UI Delete in Configuration Tab - 4 | bar: July 3; October 5 to October 9
QA - 10 | bar: July 3; October 12 to October 16; October 19 to October 23
RFS | bar: July 1 to October 28
| Merchant On-Boarding History - Nov 26 | API - 5 | bar: October 21 to October 23; October 26 to October 27
UI - integrate in Merchant and Queues - 5 | bar: October 28 to October 30; November 3 to November 7
QA - 10 | bar: November 10 to November 14; November 17 to November 21
RFS | bar: July 1 to November 26
| Expansion of Callout Queue - Nov 26 | Database - add status - 4 | bar: October 28 to October 30; November 3
UI - 10 | bar: November 4 to November 7; November 10
QA - 10 | bar: November 11 to November 14; November 17 to November 21
RFS | bar: July 1 to November 26
| Add Negative Scenario Queues | Database - add status - 4 | bar: July 3; July 6 to July 10
QA - 5 | bar: July 3; July 13 to July 17
RFS | bar: July 1 to September 16
| Additional KYM Functionalities - Oct 21 | API - Configuration for Schedule - 6 | bar: July 3; August 17 to August 21; August 24
API - Update logic of create/update business/branch - 7 | bar: August 6 to August 7; August 10 to August 14
UI - 7 | bar: August 25 to August 28; August 31 to September 4
QA - 10 | bar: September 7 to September 11; September 14 to September 18
RFS | bar: July 1 to September 23
| Move Comments Field to Business Documents Section | UI - (business - before doc) - 5 Database - 10 | bar: October 12 to October 16; October 19 to October 23; October 26 to October 30
QA - 10 | bar: November 3 to November 7; November 10 to November 14
RFS | bar: July 1 to November 19
| Add Philippine Standard Industry Classification (PSIC) Field | API - configuration for mapping - 5 | bar: July 3; September 7 to September 11
UI - configuration for mapping - 5 | bar: July 3; September 14 to September 18
UI - integrate in business information - 5 | bar: July 3; September 21 to September 25
QA - 10 | bar: September 28 to October 2; October 5 to October 9
x
| Transaction Limits | API - App - 4 | bar: November 11 to November 14
API - Admin Portal to Swiff - 5 | bar: November 17 to November 21
Android App FE- 2 | bar: July 3; November 17 to November 18
IOS App FE - 2 | bar: July 3; November 17 to November 18
QA - 10 | bar: November 24 to November 28
RFS | bar: July 1 to December 3
| Alignment of Globe Charge registration channels | API -5 | bar: July 3; August 10 to August 14
Globe Portal UI | bar: July 3
QA - 10
RFS | bar: July 1 to August 25
| LB auto-shifting APP | Android RND - 3 | bar: July 3; November 3 to November 5
Android implem - 3 | bar: July 3; November 6 to November 7; November 10 to November 14
IOS RND - 3 | bar: July 3; November 5 to November 7
IOS implem - 2 | bar: November 10 to November 14
QA - 10 | bar: November 17 to November 21
RFS | bar: July 1 to November 26

## DROPS
QA | Dex | Bhadz | July | [30 empty] | August | [30 empty] | September | [29 empty] | October | [29 empty] | November | [29 empty] | December
Dhino | Don | Globe Portal | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Drop 1 Sept 16 | Dongle | API Add - 3 | bar: July 20 to July 22
API Edit - 3 | bar: July 23 to July 24; July 27
API Delete - 3 | bar: July 28 to July 30
UI Add - 5 | bar: July 3; July 27 to July 31
UI Edit - 5 | bar: July 3; August 3 to August 7
UI Delete - 5 | bar: July 3; August 10 to August 14
API Batch Upload Dongles - 4 | bar: July 3; August 17 to August 20
UI Batch Upload Dongles - 4 | bar: August 21; August 24 to August 27
QA - 10 | bar: August 31 to September 4; September 7 to September 11
RFS | bar: July 1 to September 23
| Add Negative Scenario Queues | Database - add status - 4 | bar: July 3; July 6 to July 10
QA - 5 | bar: July 3; July 13 to July 17
RFS | bar: July 1 to September 23
Drop 2 Sept 23 | MUR | Firewall from BOSS to AWS | bar: July 6 to July 10; July 13 to July 17; July 20 to July 24; July 27 to July 31; August 3 to August 7
BOSS extract transaction report, save in DB and backup in S3 - 10 | bar: July 3; July 6 to July 10; July 13 to July 17
API Branch list - 4 | bar: July 3; July 20 to July 23
API Business list - 3 | bar: July 3; July 24; July 27 to July 28
API Advance search - 5 | bar: July 3; July 29 to July 31; August 3 to August 4
UI Branch list - 5 | bar: August 5 to August 7; August 10 to August 11
UI Business list - 5 | bar: July 3; August 12 to August 14; August 17 to August 18
UI Advance search - 10 | bar: July 3; August 19 to August 21; August 24 to August 28; August 31 to September 4
QA - 10 | bar: July 3; September 7 to September 11; September 14 to September 18
RFS | bar: July 1 to September 23
| Additional KYM Functionalities | API - Configuration for Schedule - 6 | bar: July 3; August 17 to August 21; August 24
API - Update logic of create/update business/branch - 7 | bar: July 3; August 6 to August 7; August 10 to August 14
UI - 7 | bar: July 3; August 25 to August 28; August 31 to September 4
QA - 10 | bar: July 3; September 7 to September 11; September 14 to September 18
RFS | bar: July 1 to September 23
Drop 3 Oct 15 | Add Philippine Standard Industry Classification (PSIC) Field Include MCC auto populate (Business Industry - Description - MCC) | API - configuration for mapping - 5 | bar: July 3; September 7 to September 11
UI - configuration for mapping - 5 | bar: July 3; September 14 to September 18
UI - integrate in business information - 5 | bar: July 3; September 21 to September 25
QA - 10 | bar: September 28 to October 2; October 5 to October 9
x
Drop 4 Oct 28 | Partner, Sales Channel and Account Owner Management | API - Integrate in Merchant Tab - 4 | bar: July 3; September 2 to September 4; September 7
UI - Integrate in Merchant Tab - 5 | bar: July 3; September 8 to September 11; September 14
API Add - 2 | bar: July 3; September 15 to September 16
API Edit - 2 | bar: July 3; September 17 to September 18
API Delete - 2 | bar: September 21 to September 22
UI Add in Configuration Tab - 4 | bar: September 23 to September 25; September 28
UI Edit in Configuration Tab - 4 | bar: July 3; September 29 to October 2
UI Delete in Configuration Tab - 4 | bar: July 3; October 5 to October 9
QA - 10 | bar: July 3; October 12 to October 16; October 19 to October 23
RFS | bar: July 1 to October 28
Drop 5 Nov 19 | SLA and Aging | Queues - API -10 | bar: July 3; July 6 to July 10; July 13 to July 17
Queues - UI -10 | bar: July 3; August 5 to August 7; August 10 to August 14; August 17 to August 18
Configuration SLA (Rules) - API - 20 | bar: July 3; August 19 to August 21; August 24 to August 28; August 31 to September 4; September 7 to September 11; September 14 to September 15
Configuration SLA (Rules) - UI - 20 | bar: July 3; September 16 to September 18; September 21 to September 25; September 28 to October 2; October 5 to October 9; October 12 to October 13
Merchant - API - 5 | bar: October 14 to October 16; October 19 to October 23
QA - 10 | bar: October 26 to October 30; November 3 to November 7
RFS | bar: July 1 to November 19
| Move Comments Field to Business Documents Section | UI - (business - before doc) - 5 Database - 10 | bar: October 12 to October 16; October 19 to October 23; October 26 to October 30
QA - 10 | bar: November 3 to November 7; November 10 to November 14
RFS | bar: July 1 to November 19
Drop 6 Nov 26 | Merchant On-Boarding History | API - 5 | bar: October 21 to October 23; October 26 to October 27
UI - integrate in Merchant and Queues - 5 | bar: October 28 to October 30; November 3 to November 7
QA - 10 | bar: November 10 to November 14; November 17 to November 21
RFS | bar: July 1 to November 26
| Expansion of Callout Queue | Database - add status - 4 | bar: October 28 to October 30; November 3
UI - 10 | bar: November 4 to November 7; November 10
QA - 10 | bar: November 11 to November 14; November 17 to November 21
RFS | bar: July 1 to November 26
| LB auto-shifting APP | Android RND - 3 | bar: July 3; November 3 to November 5
Android implem - 3 | bar: July 3; November 6 to November 7; November 10 to November 14
IOS RND - 3 | bar: July 3; November 5 to November 7
IOS implem - 2 | bar: November 10 to November 14
QA - 10 | bar: November 17 to November 21
RFS | bar: July 1 to November 26
Drop 7 Dec 3 | Transaction Limits | Swiff API
API - App - 4 | bar: November 11 to November 14
API - Admin Portal to Swiff - 5 | bar: November 17 to November 21
Android App FE- 2 | bar: July 3; November 17 to November 18
IOS App FE - 2 | bar: July 3; November 17 to November 18
QA - 10 | bar: November 24 to November 28
RFS | bar: July 1 to December 3
| Alignment of Globe Charge registration channels | API -5 | bar: July 3; August 10 to August 14
Globe Portal UI | bar: July 3
QA - 10
RFS | bar: July 1 to August 25
|  | Data dump to and from boss | July 1: track separately - dev done already. pending is s3 access

## Daily Monitoring
| Dexter | Bhadz | Don
2015-07-13 | Bug: 1. Photos Syn(KYM app) (Upload in portal then KYM App) Happy Meal: 1. Queues API - DB Structure target completion today 2. Negative Scenario | BOSS extract transaction report, save in DB and backup in S3 - 10 until July 14 | Bug: 1. Check if dongle sold tracker can be started